**Project plan**

**Group S**

**Project leader:** Angelica Rao – 2701871

**Quality manager:** Veselin Chumpalov – 2786877

**Chairman:** Anzhelo Iliev – 2855569

**Secretary:** Yordan Alipiev – 2764776

Table of Contents

[I. Project Statement 3](#_Toc444538014)

[1. Formal Client 3](#_Toc444538015)

[2. Project Leader 3](#_Toc444538016)

[3. Current Situation 3](#_Toc444538017)

[4. Problem Description 3](#_Toc444538018)

[5. Project Goal 3](#_Toc444538019)

[6. Project Deliverables and Non-deliverables 3](#_Toc444538020)

[7. Project Constraints 3](#_Toc444538021)

[8. Project Risks 3](#_Toc444538022)

[II. Project Phasing 3](#_Toc444538023)

[III. References 3](#_Toc444538024)

# Project Statement

## Formal Client

The formal client for this project is Mr. Vladimir Kabzar. He is the CEO of *“Global Solutions Inc”.* He has hired Dream Team to organize a social event for his company. He is the one who can take important decisions if necessary.

Contact information:  
Vladimir Kabzar  
Eindhoven, the Netherlands  
Email: v.kabzar@fontys.nl  
Phone: (+31) 6 5678 9988

## Project Leader

The project leader is Angelica Rao, a first-year student at Fontys University of Applied Sciences. She specializes in Information, Communication and Technology & Software Engineering in the English Stream of the University. She is responsible for all communication between the project participants and the external parties.

Contact information:   
Angelica Rao  
Eindhoven, the Netherlands  
Email: [a.rao@student.fontys.nl](mailto:a.rao@student.fontys.nl)  
Phone: (+31) 6 – 3844 7792

## Current Situation

There are many festivals in the Netherlands but none of them includes music, water and greeting the sun. Our client wants to establish а new cultural movement and show the Western Europeans some Eastern traditions in а fun remarkable way. He wants from us to organize the event, pick name and create the logo, the web page, the applications, any other software that might be needed and the payment methods which are necessary for the proper holding of the event.

## Problem Description

The client doesn’t have the opportunity to create the event by himself so he decided to ask for help from the Dream-Team. To establish such an event we are required to begin a research in many spheres of the tourist, software and technology industry, to develop a general plan for the event, calculate the required resources and come up with a final product. To manage to do that we have to have many discussions with the client about his idea and what exactly he wants.

## Project Goal

## Project Deliverables and Non-deliverables

## Project Constraints

## Project Risks

# Project Phasing

# References